## Sheet1
TASKS | Number Of Days | Resources | Start | End | Sprint Days | Total Points
Sprint 0 – Kick Off, Planning, Research and Logistics |  |  | 2018-09-17 |  | 15 | 381
CSG Introduction to InfoTRANSIT Architecture (Ongoing) 1. Architectural Introduction to System 2. Review Help system and Manuals 3. Demo of Various Features of Existing Background system 4. Jira,Confluence Training, Logins and management | 2 | Natraj, Tamanna
Research and Study Background System Architecture(Ongoing) | 5 | Natraj, Tamanna
Backlog Grooming features, PBIs and Tasks (Ongoing) | 3 | Natraj, Tamanna
Sprint 1 – System Architecture , Prototype Rest Operations |  |  | 2018-10-02
Backlog Grooming features, PBIs and Tasks (Ongoing) CSG Support and Training | 2 | Natraj, Tamanna
Polymer 3 – Understand Architecture and Interfacing elements, events, binding and cache management | 5 | Natraj, Tamanna
Research and Study Background System Architecture (ongoing) | 3 | Natraj, Tamanna
Get Mock Data From Jessie Team | 1 | Natraj, Tamanna
Sprint 2 – Background System Development |  |  | 2018-10-17
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Natraj, Tamanna | Line up with providing API to JO team
(Gorba - Current System) Study Web Media, Assets Service and Http-Service Application and Interactions with New Background System (Ongoing) | 5 | Natraj, Tamanna
Prototype Background System Architecture (Requirements/Setup/Install/Deploy) of the new Background System Applying Assets Services | 3 | Natraj, Tamanna
Testing | 4 | CSG
Sprint 3 – Interface with JO Team Jasper UI |  |  | 2018-11-01
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Natraj, Tamanna
Define and Implement security and authentication using https (Membership Service) | 5 | Natraj
Planning Continues Integration and Continues Deployment | 3 | Tamanna
Create Prototype Rest Api End Points and Expose it with Swagger Using Backend Architecture | 5 | Natraj
Granite Dashboard ( Jasper) • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Define Rest API for Recent Browse presentation • Define Rest API for Recent Browse Asset • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 3 | Natraj
Testing | 4 | CSG
Provide API for initial access to real data | 1 |  | 2018-11-15
Sprint 4 – Asset Management Service (Temporary Service Before Marble) |  |  | 2018-11-16
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Jasper (Granite) Sign In Page • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Integrate authentication with the background server. • Use existing Database schema for user • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 5 – Jasper Media File Assets Serialization and Deserialization |  |  | 2018-12-01
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Jasper (Granite) Sign In Page • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Integrate authentication with the background server. • Use existing Database schema for user • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 5 – Jasper Media File Processing |  |  | 2018-12-16
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Media File Processing (Study Architecture and Planning) • Design and Map Jasper UI attributes and Properties to Media Files • Filter out non-required data schema Formula/RegEx • Design File Schema for Operations based on existing media file | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 6 – Jasper Media File Design and Development |  |  | 2018-12-31
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Media File Processing (Debug and Development) • Design and Map Jasper UI attributes and Properties to Media Files • Filter out non-required data schema Formula/RegEx • Design File Schema for Operations based on existing media file | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 7 – Presentation Browser and Selection |  |  | 2019-01-15
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Presentation Browser/Selection Page: • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Connection with background server and database • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 5 | Tamanna
CI & CD Deploy of the new Background System and APIs | 3 | Tamanna and Natraj
Docker and Azure Architecture Development | 5 | Natraj
Testing | 4 | CSG
Sprint 8 - Presentation Sequence Page Integration |  |  | 2019-01-30
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2
Presentation Sequence Preview Page: • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8
Testing | 4 | CSG
Sprint 9 – New Presentation Dashboard |  |  | 2019-02-14
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Design and Develop the Asset Management Service • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define DB Schema for asset: Serialize and De-serialize • Create an Rest API interface and Prototype • Rest API Jason mapping to Classes • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Natraj
Develop the Integration with New Presentation Dashboard • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define DB Schema for asset: Serialize and De-serialize • Create an Rest API interface and Prototype • Rest API Jason mapping to Classes • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna
Testing | 4 | CSG
Sprint 10 – Edit Presentation Dashboard |  |  | 2019-03-01
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Develop the Integration with Edit Presentation Dashboard • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define DB Schema for asset: Serialize and De-serialize • Create an Rest API interface and Prototype • Rest API Jason mapping to Classes • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Sprint 11 – Asset Management Editor Integration |  |  | 2019-03-16
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Asset Management Editor Interfacing: • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 12 – Asset Management Selection and Drag |  |  | 2019-03-31
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Asset Management Selection • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Natraj
Asset Management Drag • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna
Testing | 4 | CSG
Sprint 13 – Presentation Master Cycle – Screen Selections |  |  | 2019-04-15
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Master Cycle – Screen Selected • Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8
Testing | 4 | CSG
Sprint 14 – Presentation Master Cycle – Full Master Cycle |  |  | 2019-04-30
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Sprint 15 – Presentation Master Cycle – Asset Editor |  |  | 2019-05-15
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 16 – Presentation Off Route Event |  |  | 2019-05-30
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 17 – Proximity to a Point Part I |  |  | 2019-06-14
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 18 – Proximity to a Point Part II |  |  | 2019-06-29
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 19 – Asset Route Ladder Editing |  |  | 2019-07-14
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
• Identify, Define and Create Models and Attributes • Create Sample / Mock Data • Define Rest Operations End Points (Crud and Query) • Create Swagger UI for Testing • Refine Data Models – Integration to UI • Testing End Points for Functionality, Load and Latency | 8 | Tamanna and Natraj
Testing | 4 | CSG
Sprint 20 – IAdmin Compatibility With Saving and Loading Presentations |  |  | 2019-07-29
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Save Presentation in Media and Load it in Jasper | 3
Load Presentations Created in Jasper into Iadmin | 5 | Tamanna and Natraj
Testing | 8 | CSG
Sprint 21 – Integration Testing |  |  | 2019-08-13
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
TBD | 8 | Tamanna and Natraj
Testing | 8 | CSG
Sprint 22 – Integration Testing and Bug Fixes |  |  | 2019-08-28
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
Changes based on Testing | 8
Testing | 8 | CSG
Sprint 23 – Production Deployment and Testing |  |  | 2019-09-12
Analysis and Design of PBIs and Tasks (Ongoing) CSG Management, Monitoring and Tasks | 2 | Tamanna and Natraj
TBD | 8 | Tamanna and Natraj
Release | 8 | Tamanna and Natraj
2019-09-27
Note on H1: Natraj Bontha: Sprint Days(14) + 1 day for planning and review